| DATE | ACTIVITIES (subject to change) | Preparation Needed | OUTCOME(S) |
| --- | --- | --- | --- |
| 8/18/03 | Organizational meeting to revise and adopt the ground rules & work plan. Introductory grounding in process and relationships. | Draft ground rules for review to staff and Commission members. | Adopt Ground Rules & Work Plan (this document). Increase understanding of participant’s interests public schools in Montana. |
| 9/8/03 | Identify two issues that the Commission will address and what information will be needed. | Line up resource people to present overview and have copies of handouts available to commission members in advance of meeting. The Commission will consider key questions they have, why it’s important to answer those questions, what data is needed to answer those questions from where, by whom and whether or not it’s practical to answer those questions by the next meeting date. | Overview information presented on issues 2.1 (b) & (c). Commission discussion of info. |
| 9/29/03 | Identify 2-3 issues that the Commission will address and what information will be needed | Line up resource people and have copies of handouts available to commission members in advance of meeting. | There will be more mutual understanding about the issues and data needed to make recommendations. In addition, points of disagreement will be more sharply defined by the Commission with strategies to address those points of disagreement or set them aside (agree to disagree). |
| 10/13/03 | Discussion of – What is the definition of a basic system of free, quality public elementary and secondary education in Montana? |  |  |
| 11/3/03 | How can the basic system be provided? Work on options. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| 11/24/03 | Discussion of – Do we have a system that is providing adequate education to every student in Montana? |  |  |
| 12/08/03 | What are options for providing an adequate education. Consider criteria for narrowing options. Seek preliminary agreement |  |  |
| Jan, ‘04 | Discussion of – Do we have adequate funding to fund public education. Are we providing it now? |  |  |
| Feb. ‘04 | What are options for providing adequate funding to fund public education. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| Late Fed. ‘04 | What is the states’ obligation to provide a quality public education to all students in MT? |  |  |
| March ‘04 | What are the states’ options to meet its obligation. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| Late March ‘04 | Discussion of how to develop a predictable and sustainable system of funding. |  |  |
| April ‘04 | Explore options for developing a predictable and sustainable system of funding. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| Late April ‘ 04 | Discussion of – How do we develop a simpler, more understandable system than we current have? |  |  |
| May ‘04 | Develop criteria and apply to options generated. Seek preliminary agreement |  |  |
| Late May ‘04 | Discussion of – Is there a problem with having the current structure of local and state governance? |  |  |
| June ‘04 | Develop options for addressing structure. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| Late June ‘04 | Discussion of – Is there a problem with the tax system? |  |  |
| July ‘04 | Develop options for addressing problems with the tax system. Consider criteria for narrowing options. Seek preliminary agreement. |  |  |
| Aug. ‘04 | Discussion of other need questions that arise. Draft written recommendations |  |  |
|  | Review draft recommendations |  |  |
| 9/15/04 |  |  | Submit final report of findings and recommendation to the education and local government interim committee. |